## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name | Group 28 |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Xiangyu Zhong
Project Start Date: | 2023-06-16 |  |  |  |  | June | [13 empty] | July | [27 empty] | August
Scrolling Increment: | 4 | time axis 2023-06-20 to 2023-08-14
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-06-20 to 2023-08-14
Process 1
User requirements collection | Low Risk | Xiangyu Zhong | 30% | 2023-06-16 | 10
Requirements collection | Milestone | Xiangyu Zhong | 45% | 2023-06-21 | 1 | bar: 2023-06-21
Analysis design | Low Risk | Xiangyu Zhong | 50% | 2023-06-13 | 10
Prototype review | Milestone | Xiangyu Zhong | 35% | 2023-07-06 | 5 | bar: 2023-07-06 to 2023-07-10
Acceptance design | Med Risk | Xiangyu Zhong | 20% | 2023-06-22 | 6
Process 2
Types of Design Tutorials: | High Risk | Xiangyu Zhong | 50% | 2023-06-22 | 13
Determine product priority | On Track | Xiangyu Zhong | 60% | 2023-06-24 | 9
Develop release plans and iteration plans | Low Risk | Xiangyu Zhong | 33% | 2023-06-29 | 11
Reviewing the strengths and weaknesses of other similar open-source projects. | Milestone | Xiangyu Zhong | 15% | 2023-07-01 | 1 | bar: 2023-07-01
|  |  | 60% | 2023-07-02
Process 3
Check the website running status | On Track | Xiangyu Zhong | 30% | 2023-07-01 | 4
Optimize website | Med Risk | Xiangyu Zhong | 67% | 2023-07-04 | 14
Test the website and find errors in it | On Track | Xiangyu Zhong | 35% | 2023-07-19 | 6
Correct collected errors | Goal | Xiangyu Zhong | 20% | 2023-07-23 | 3 | 2023-07-23: 2; 2023-07-24: 2; 2023-07-25: 2
|  |  | 80% | 2023-06-22
Process 4
Insufficient statistics and correction | Low Risk | Xiangyu Zhong | 65% | 2023-07-26 | 19
Identify customers and collect data | Med Risk | Xiangyu Zhong | 30% | 2023-08-09 | 5
Accept customer feedback | Milestone | Xiangyu Zhong | 40% | 2023-08-10 | 1 | bar: 2023-08-10
Provide solutions to customer problems | Med Risk | Xiangyu Zhong | 35% | 2023-07-28 | 5
Task 5
To add more data, Insert new rows ABOVE this one
Formulas:
Group 28 = IFERROR(IF(MIN(Milestones4352[Start])=0,TODAY(),B11(Milestones4352[Start])),TODAY())

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-06-16 |  |  |  |  | June | [13 empty] | July | [34 empty] | August
Scrolling Increment: | 1 | time axis 2023-06-17 to 2023-08-11
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2023-06-16 | 3 | S: 2; S: 2
Task 2 | Milestone |  |  | 2023-06-21 | 1 | bar: W
Task 3 | Low Risk |  | 50% | 2023-06-13 | 10
Task 4 | Milestone |  |  | 2023-07-06 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2023-06-22 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-06-22 | 13
Task 2 | On Track |  | 50% | 2023-06-24 | 9
Task 3 | Low Risk |  | 33% | 2023-06-29 | 11
Task 4 | Milestone |  |  | 2023-07-01 | 1 | bar: S
Task 5 |  |  |  | 2023-07-02 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-07-01 | 4
Task 2 | Med Risk |  |  | 2023-07-04 | 14
Task 3 | On Track |  |  | 2023-07-19 | 6
Task 4 | Goal |  |  | 2023-07-23 | 3 | S: 2; M: 2; T: 2
Task 5 | Low Risk |  |  | 2023-06-22 | 19
TITLE 4
Task 1 |  |  |  | 2023-07-26 | 15
Task 2 |  |  |  | 2023-08-09 | 5
Task 3 | Milestone |  |  | 2023-09-20 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2023-06-16 |  |  |  |  | June | [13 empty] | July | [27 empty] | August
Scrolling Increment: | 5 | time axis 2023-06-21 to 2023-08-15
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-06-21 to 2023-08-15
TITLE 1
Task 1 | Goal | Name | 25% | 2023-06-16 | 3
Task 2 | Milestone |  |  | 2023-06-21 | 1 | bar: 2023-06-21
Task 3 | Low Risk |  | 50% | 2023-06-13 | 10
Task 4 | Milestone |  |  | 2023-07-06 | 1 | bar: 2023-07-06
Task 5 | Med Risk |  | 10% | 2023-06-22 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-06-22 | 13
Task 2 | On Track |  | 50% | 2023-06-24 | 9
Task 3 | Low Risk |  | 33% | 2023-06-29 | 11
Task 4 | Milestone |  |  | 2023-07-01 | 1 | bar: 2023-07-01
Task 5 |  |  |  | 2023-07-02 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-07-01 | 4
Task 2 | Med Risk |  |  | 2023-07-04 | 14
Task 3 | On Track |  |  | 2023-07-19 | 6
Task 4 | Goal |  |  | 2023-07-23 | 3 | 2023-07-23: 2; 2023-07-24: 2; 2023-07-25: 2
Task 5 | Low Risk |  |  | 2023-06-22 | 19
TITLE 4
Task 1 |  |  |  | 2023-07-26 | 15
Task 2 |  |  |  | 2023-08-09 | 5
Task 3 | Milestone |  |  | 2023-09-20 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one